## Project Timeline
ID | Phase | Task | Start Date | End Date | Duration (days) | Parallel / Sequencing Notes | Status | Deliverable / Notes
1 | Phase 0 – Setup & Literature | Learn Git & GitHub basics (init, add, commit, push, .gitignore, README, basic branching); create the GitHub repository (L1) | 2026-09-23 | 2026-09-24 | 1 | — | Done | Do this before writing a single line of project code — see chat for the concrete repo structure.
2 | Phase 0 – Setup & Literature | Learn Python fundamentals coming from MATLAB: syntax, NumPy arrays & 0-based indexing, functions, control flow (L2) | 2026-09-23 | 2026-09-27 | 4 | Parallel with Tasks 1, 3, 4, 5 | In progress | No prior Python experience assumed — budget real time for this.
3 | Phase 0 – Setup & Literature | Set up Python environment (venv), VS Code + Jupyter integration, requirements.txt; build folder structure inside the repo (dynamics/, mpc/, sim/, tests/, docs/, notebooks/); first commit | 2026-09-24 | 2026-09-26 | 2 | After Task 1 | Done
4 | Phase 0 – Setup & Literature | Read 3–4 recent LA3 (Colin Jones) papers + skim rendezvous/ADR MPC literature (survey-level) | 2026-09-23 | 2026-10-02 | 9 | Parallel with Tasks 1, 2, 3 | Not started | This is what makes the motivation letter specific instead of generic.
5 | Phase 0 – Setup & Literature | Study linear systems & state-space representation (L3) | 2026-09-23 | 2026-09-28 | 5 | Parallel with Tasks 1–4 | Not started
6 | Phase 0 – Setup & Literature | Study CW derivation, assumptions, forced response & ZOH discretization theory (L4) | 2026-09-26 | 2026-10-03 | 7 | Parallel with Task 4, after Task 5 | Not started
7 | Phase 1 – Translational Dynamics (3-DoF) | Derive continuous-time CW state-space model (A, B) in LVLH frame, including the control-acceleration input; write-up per L19 | 2026-09-29 | 2026-10-03 | 4 | — | Not started | Math write-up before any code.
8 | Phase 1 – Translational Dynamics (3-DoF) | Discretize (ZOH / state transition matrix), implement propagator | 2026-10-03 | 2026-10-06 | 3 | — | Not started
9 | Phase 1 – Translational Dynamics (3-DoF) | Unit tests: propagator vs. analytic CW solution (free-drift ellipse check) | 2026-10-06 | 2026-10-08 | 2 | — | Not started | First real test in tests/ — not optional.
10 | Phase 1 – Translational Dynamics (3-DoF) | Study state estimation / noise modeling basics (L5), then add Gaussian process + measurement noise to the sim, with a basic Kalman filter feeding the controller | 2026-10-06 | 2026-10-09 | 3 | Parallel with Task 9 tail | Not started | Without this, the whole project assumes perfect knowledge — a real weak point. If time is tight, the minimal KF can slip to just before Task 20.
11 | Phase 1 – Translational Dynamics (3-DoF) | Build nonlinear two-body plant (sim/) + CW-vs-nonlinear sweep over target eccentricity e and separation ρ (L20); short write-up: CW linearization assumptions & validity limits | 2026-10-08 | 2026-10-11 | 3 | Parallel with Task 10 and start of Task 12 | Not started | Goes in docs/ — one page is enough. Sweep above SL-16's e≈1e-3 is a stress test, label it as such. End date moved 9→11 Oct; Phase 2 opens with study tasks, so no critical-path impact.
12 | Phase 2 – Linear MPC (Translational) | Study convex optimization fundamentals (L6) | 2026-10-09 | 2026-10-13 | 4 | Parallel with Task 13 start | Not started
13 | Phase 2 – Linear MPC (Translational) | Study MPC theory: receding horizon, cost design, terminal ingredients, stability intro (L7) | 2026-10-12 | 2026-10-18 | 6 | — | Not started
14 | Phase 2 – Linear MPC (Translational) | Formulate QP/SOCP: cost function, horizon N, thrust constraints, keep-out / approach-cone constraints (hard) — convex modeling per L21 | 2026-10-18 | 2026-10-21 | 3 | — | Not started | Write the formulation doc before opening CVXPY.
15 | Phase 2 – Linear MPC (Translational) | Study soft constraints & recursive feasibility basics (L8) | 2026-10-18 | 2026-10-23 | 5 | Parallel with Task 14 | Not started
16 | Phase 2 – Linear MPC (Translational) | Extend formulation with soft constraints (slack variables) for guaranteed feasibility | 2026-10-21 | 2026-10-23 | 2 | — | Not started | Talking point #1 for the interview.
17 | Phase 2 – Linear MPC (Translational) | Study CVXPY practical usage (L9) | 2026-10-21 | 2026-10-23 | 2 | Parallel with Task 16 | Not started
18 | Phase 2 – Linear MPC (Translational) | Implement linear MPC in CVXPY (nominal, noiseless case) | 2026-10-23 | 2026-10-26 | 3 | — | Not started
19 | Phase 2 – Linear MPC (Translational) | Closed-loop nominal simulation + core metrics (fuel/Δv consumption, settling time, constraint violations) | 2026-10-26 | 2026-10-28 | 2 | — | Not started | First real deliverable — usable in CV/interview from here.
20 | Phase 2 – Linear MPC (Translational) | Closed-loop Monte Carlo simulation under navigation noise + CW-vs-plant mismatch (dispersion plots, robustness check; L22) | 2026-10-28 | 2026-10-30 | 2 | — | Not started | Talking point #2: how the controller degrades under realistic uncertainty.
21 | Phase 2 – Linear MPC (Translational) | Unit tests for MPC module (feasibility checks, solver status handling) | 2026-10-30 | 2026-10-31 | 1 | Parallel with Task 22 | Not started
22 | Phase 2 – Linear MPC (Translational) | Document Phase 1–2 results (plots, metrics table) in repo README/report | 2026-10-30 | 2026-11-01 | 2 | Parallel with Task 21 | Not started | This is what you screen-share if interviewed early.
23 | Application (parallel track) | Align motivation letter language with LA3 + shortlisted labs' recent papers | 2026-10-01 | 2026-10-15 | 14 | Parallel with Phase 0–1 | Not started
24 | Application (parallel track) | Draft CV bullets + motivation letter using Phase 1–2 results/plots | 2026-10-16 | 2026-10-28 | 12 | Parallel with Phase 2 tail | Not started
25 | Application (parallel track) | MILESTONE: Submit E3 application (up to 3 lab choices, CV, transcripts, statement of purpose, ID) | 2026-11-01 | 2026-11-01 | 0 | Hard deadline — confirmed on eee.epfl.ch | Not started | Portal opens Oct 2026, closes Nov 1, 2026.
26 | Application (parallel track) | Keep GitHub repo continuously updated & interview-ready (rolling — do not batch this at the end) | 2026-11-01 | 2027-03-01 | 120 | Runs in parallel with everything below | Not started | Interviews can happen any time Nov–early Mar — the repo must be presentable throughout, not just in January.
27 | Phase 3 – Rotational Dynamics (3-DoF) | Study attitude kinematics & dynamics: quaternions/MRPs, Euler's equations (L10) | 2026-11-01 | 2026-11-08 | 7 | — | Not started
28 | Phase 3 – Rotational Dynamics (3-DoF) | Formulate nonlinear attitude dynamics | 2026-11-08 | 2026-11-12 | 4 | — | Not started
29 | Phase 3 – Rotational Dynamics (3-DoF) | Linearize (small-angle / MRP) for use inside a linear MPC (L11) | 2026-11-10 | 2026-11-13 | 3 | Parallel with Task 28 tail | Not started
30 | Phase 3 – Rotational Dynamics (3-DoF) | Unit tests: attitude propagator validation | 2026-11-13 | 2026-11-14 | 1 | — | Not started
31 | Phase 4 – Rotational MPC | Study RW/RCS actuator constraints & torque allocation basics (L12) | 2026-11-14 | 2026-11-20 | 6 | — | Not started
32 | Phase 4 – Rotational MPC | Formulate attitude MPC (torque/momentum saturation, soft constraints where needed) | 2026-11-20 | 2026-11-24 | 4 | — | Not started
33 | Phase 4 – Rotational MPC | Implement + closed-loop detumble/pointing simulation + metrics | 2026-11-24 | 2026-11-28 | 4 | — | Not started
34 | Phase 4 – Rotational MPC | Monte Carlo robustness test under attitude estimation noise | 2026-11-28 | 2026-12-01 | 3 | — | Not started
35 | Phase 4 – Rotational MPC | PORTFOLIO CHECKPOINT #1: integrate translational + rotational results into one unified report | 2026-12-01 | 2026-12-04 | 3 | — | Not started | Safe fallback deliverable if the interview happens before Phase 5 is mature.
36 | Phase 5 – Nonlinear Coupled 6-DoF MPC | Study NMPC theory: multiple shooting, direct collocation, SQP/interior-point basics (L13) | 2026-12-04 | 2026-12-15 | 11 | — | Not started
37 | Phase 5 – Nonlinear Coupled 6-DoF MPC | Study CasADi practical usage + example patterns (L14) | 2026-12-10 | 2026-12-20 | 10 | Parallel with Task 36 tail | Not started
38 | Phase 5 – Nonlinear Coupled 6-DoF MPC | Study solver internals: why OSQP/ECOS for QP vs. IPOPT for NLP, warm-starting (L15) | 2026-12-15 | 2027-01-05 | 21 | Parallel with Task 37 / holidays | Not started
39 | Phase 5 – Nonlinear Coupled 6-DoF MPC | Formulate coupled nonlinear 6-DoF model (translation–rotation coupling via docking-port offset; L23) | 2027-01-05 | 2027-01-15 | 10 | — | Not started | This is the 'frontier' you present as in-progress at the interview.
40 | Phase 5 – Nonlinear Coupled 6-DoF MPC | Implement NMPC in CasADi (multiple shooting), first working closed-loop test case | 2027-01-15 | 2027-02-01 | 17 | — | Not started | A rough working version is enough — do not over-polish before validating it works at all.
41 | Phase 5 – Nonlinear Coupled 6-DoF MPC | Full validation suite: Monte Carlo over initial conditions + noise, metrics table, solver-time stats | 2027-02-01 | 2027-02-12 | 11 | — | Not started
42 | Phase 5 – Nonlinear Coupled 6-DoF MPC | Recursive feasibility / terminal set discussion — analytical or qualitative write-up | 2027-02-10 | 2027-02-18 | 8 | Parallel with Task 41 tail | Not started | Even a qualitative discussion is a strong interview talking point.
43 | Phase 5 – Nonlinear Coupled 6-DoF MPC | PORTFOLIO CHECKPOINT #2: full 6-DoF results integrated into repo + report | 2027-02-18 | 2027-02-25 | 7 | No hard deadline — extend if needed, this is research-grade work | Not started | It is fine — expected, even — for this to still be open at interview time.
44 | Phase 6 – Stretch Goals (optional) | Study robust / tube MPC concepts (L17) — directly ties to LA3's own research | 2027-02-25 | 2027-03-10 | 13 | — | Not started
45 | Phase 6 – Stretch Goals (optional) | Explore a robust or tube-based MPC extension on the translational subsystem | 2027-03-10 | 2027-03-24 | 14 | — | Not started | Optional — only if Phase 5 finished with time to spare.
46 | Phase 6 – Stretch Goals (optional) | Optional: simple synthetic vision-based relative pose estimation module (closes the GNC sense loop; L24) | 2027-03-24 | 2027-04-10 | 17 | Can run parallel with Task 45 | Not started | Relevant if targeting Cavallaro/LIDIAP as a lab choice — see Target Labs sheet.
47 | Phase 6 – Stretch Goals (optional) | Optional: learning-based MPC exploration (e.g. Gaussian process or NN model-mismatch correction; L25) | 2027-04-10 | 2027-04-30 | 20 | — | Not started | Ties back to your original AI/ML interest without abandoning the control core.
48 | Phase 6 – Stretch Goals (optional) | Prepare a short conference-style write-up/poster of the full project as a standalone portfolio artifact | 2027-04-30 | 2027-05-15 | 15 | — | Not started | Good to have before the internship itself starts (May–Oct 2027).
49 | Interview Prep (parallel track) | Prepare talking points: CW → linear MPC → 6-DoF NMPC narrative, open problems, stability/feasibility discussion | 2026-11-01 | 2026-11-15 | 14 | Parallel with Phase 3 start — do this early, interviews can start mid-Nov | Not started
50 | Interview Prep (parallel track) | Mock technical interview (self Q&A or with a peer/professor) | 2026-11-15 | 2026-11-22 | 7 | — | Not started | Repeat again in Jan/Feb if the interview hasn't happened yet.
51 | Interview Prep (parallel track) | Lab-specific Q&A prep: re-read papers of whichever lab actually invites you, anticipate questions | 2026-11-22 | 2027-03-01 | 99 | Rolling — triggered by an actual interview invite, not a fixed date | Not started | See Target Labs sheet for the shortlist.
52 | Results | MILESTONE: E3 results communicated by EPFL | 2027-03-15 | 2027-03-15 | 0 | — | Not started | Confirm exact date on eee.epfl.ch — currently 'around mid-March 2027' per official FAQ.
Legend:
Shaded rows = milestones/deadlines (fixed dates, not flexible tasks)
Progress summary:
| Tasks done | 2
| Tasks in progress | 1
| Tasks not started | 49
| % complete | 3.846%

## Learning Plan
ID | Topic | Needed For (Project Task) | Study By Date | Resource(s) | Status
1 | Git & GitHub fundamentals: init, add, commit, push, .gitignore, README, basic branching | Task 1 (repo setup) — before writing any project code | 2026-09-24 | GitHub's official 'Hello World' guide (docs.github.com); Git Handbook / Pro Git book ch. 1–2 (free, git-scm.com/book) | Done
2 | Python fundamentals for MATLAB users: syntax, NumPy arrays & 0-based indexing, functions, control flow, list/dict basics | Task 3 (environment setup) and everything after — first time using Python | 2026-09-27 | NumPy official 'NumPy for MATLAB users' guide (numpy.org); Python official tutorial ch. 3–4 (docs.python.org) | In progress
3 | Linear systems & state-space representation (A, B matrices, controllability), matrix exponential, forced response (variation-of-constants formula) | Task 7 (CW state-space formulation) | 2026-09-28 | Åström & Murray, 'Feedback Systems': ch. 5 (linear systems: matrix exponential, convolution/forced response) and §6.1 (reachability); ch. 2–4 as background only. Verify numbering against your edition. Second source: Wie §2.5 (Modern State-Space Methods) and §1.3. Or your intro control course notes. | Not started
4 | Clohessy-Wiltshire equations: derivation, assumptions, forced response with control acceleration, ZOH discretization (A_d, B_d), impulsive vs. continuous thrust | Tasks 7–8 (CW model + discretization); Task 6 (study) | 2026-10-03 | Curtis ch. 7 §7.4 (CW equations, state transition matrix Φ — homogeneous solution only, no control input); Wie §4.6 (Orbital Rendezvous) for CW. Wie §2.4 (ZOH) is Laplace-domain only — skip it. ZOH / sampling with input: Åström & Wittenmark 'Computer-Controlled Systems' (sampling of continuous-time systems) or, preferred, Franklin, Powell & Workman 'Digital Control of Dynamic Systems': §4.3.3 (state-space form of the ZOH discretization, Φ and Γ) and §4.3.5 (numerical computation of Φ and Γ). Their Φ, Γ = your A_d, B_d. Skip the z-transform sections. Practice: expm of augmented matrix [[A,B],[0,0]]·dt, check vs. closed-form Φ. | Not started
5 | State estimation & noise modeling basics: process/measurement noise, discrete Kalman filter (implement the LTI case so the MPC acts on an estimated state) | Task 10 (adding realistic navigation uncertainty) | 2026-10-08 | Simon, 'Optimal State Estimation', ch. 1–5 (or any intro Kalman filter tutorial, e.g. Welch & Bishop's classic KF tutorial, UNC). Practice: write a 6-state KF on the CW model. | Not started
6 | Convex optimization fundamentals: convex sets/functions, QP structure, why convexity matters for solvers | Task 14 (QP formulation for linear MPC) | 2026-10-13 | Boyd & Vandenberghe, 'Convex Optimization', ch. 1–4 (free PDF); Stanford EE364a lecture videos | Not started
7 | MPC theory: receding horizon principle, cost function design, prediction matrices (condensed vs. sparse formulation), LQR / DARE for the terminal cost, terminal set, stability intro | Tasks 14, 18–19 (Linear MPC formulation + implementation) | 2026-10-18 | Rawlings, Mayne & Diehl, 'Model Predictive Control: Theory, Computation, and Design' (free PDF), ch. 1–2 (ch. 1 has the LQR/prediction-matrix material). Practice: scipy.linalg.solve_discrete_are for P; compare unconstrained MPC with LQR as a sanity check. | Not started
8 | Soft constraints & recursive feasibility in MPC (slack variables, exact penalty functions) | Task 16 (soft-constrained MPC) | 2026-10-21 | Rawlings/Mayne/Diehl ch. 2 (constraint handling) + ch. 3 intro; Kerrigan & Maciejowski, 'Soft constraints and exact penalty functions in MPC' (paper, freely searchable). Study-by moved from 23 Oct to 21 Oct: Task 16 starts 21 Oct. | Not started
9 | CVXPY practical usage: problem setup, parameters vs. variables, solving MPC in a loop | Task 18 (Linear MPC implementation) | 2026-10-23 | cvxpy.org official tutorial + examples gallery (MPC example specifically) | Not started
10 | Attitude kinematics & dynamics: quaternions or MRPs, Euler's rotational equations of motion | Task 27–28 (rotational dynamics formulation) | 2026-11-08 | Schaub & Junkins, 'Analytical Mechanics of Space Systems', ch. 3–4; Wie ch. 5 (§5.4 quaternions, §5.5 kinematic differential equations) and ch. 6 (§6.4 Euler's rotational equations, §6.10 rigid body in a circular orbit). | Not started
11 | Linearization techniques for attitude models (small-angle, MRP linearization) for use inside a linear MPC | Task 29 (linearized attitude state-space model) | 2026-11-13 | Schaub & Junkins ch. 4; Wie ch. 5 (kinematics, for the linearization) and §7.3 (quaternion-feedback reorientation, as classical baseline vs. the MPC). | Not started
12 | Reaction wheel / RCS actuator constraints: torque/momentum saturation, allocation basics | Task 31–32 (rotational MPC with actuator constraints) | 2026-11-20 | Wie, 'Space Vehicle Dynamics and Control': §7.4 (attitude control and momentum management: wheel torque/momentum saturation), §7.6 (optimal jet selection logic, for RCS allocation). §7.5 (CMG) not needed. | Not started
13 | Nonlinear programming for control: direct multiple shooting, collocation, SQP/interior-point basics | Tasks 36, 39 (NMPC formulation) | 2026-12-15 | Diehl & Gros, 'Numerical Optimal Control' (free PDF, syscop.de); Rawlings/Mayne/Diehl ch. 8 | Not started
14 | CasADi practical usage: symbolic modeling, nlpsol, multiple-shooting implementation pattern | Task 40 (NMPC implementation) | 2026-12-20 | casadi.org 'Getting started' + official example pack (rocket/robot MPC examples) | Not started
15 | Solver internals: QP solvers (OSQP, ECOS) vs. NLP solvers (IPOPT), warm-starting, why the choice matters | Tasks 38, 40 — and a common interview question | 2027-01-05 | OSQP paper (Stellato et al., free); IPOPT documentation intro; CasADi docs section on solver plugins | Not started
16 | MPC stability & recursive feasibility in depth (Lyapunov-based terminal ingredients) + invariant sets / terminal set computation | Task 42 + Task 49 (interview talking points) | 2026-11-15 | Rawlings/Mayne/Diehl, ch. 2–3 (stability chapters) — read a first pass early (by mid-Nov) since interviews can start then; revisit before Task 42. Invariant sets: Blanchini & Miani, 'Set-Theoretic Methods in Control' (recognize the vocabulary); MPT3 toolbox docs (mpt3.org) for intuition on invariant-set computation. | Not started
17 | Robust / tube MPC — conceptual overview (Prof. Jones' group works on this; recognize the vocabulary) | Task 44 + interview talking points | 2026-10-15 | Rawlings/Mayne/Diehl ch. 3 (robust MPC section); skim 2–3 recent LA3 (Colin Jones) papers on epfl.ch/labs/la3. Study-by moved from 20 Nov to 15 Oct: the conceptual pass has to feed the motivation letter (Task 23, 1–15 Oct) and the 1 Nov submission. Refine in Phase 6. | Not started
18 | Scientific Python toolkit & testing: matplotlib for report-quality plots, SciPy (linalg.expm, integrate.solve_ivp), pytest + numpy.testing.assert_allclose (tolerances), Jupyter workflow | Tasks 3, 8, 9, 21 (first code + first tests in tests/) | 2026-10-02 | matplotlib official tutorials ('Quick start'); SciPy docs for scipy.linalg.expm and scipy.integrate.solve_ivp; pytest 'Get started' (docs.pytest.org); NumPy docs for numpy.testing. | Not started
19 | Technical documentation: LaTeX (or Markdown with math) for formulation docs, equation/figure conventions, README structure | Tasks 7, 11, 14, 22, 35 (math write-ups before code) | 2026-09-30 | Overleaf 'Learn LaTeX in 30 minutes' + amsmath basics; or GitHub docs on math in Markdown. Half a day is enough. | Not started
20 | Nonlinear relative dynamics & numerical propagation: inertial two-body propagation, inertial→LVLH transform of the relative state, effect of target eccentricity, J2 / differential drag as optional plant perturbations (plant vs. controller-model mismatch) | Tasks 9, 11, 20 (nonlinear plant, CW-vs-nonlinear sweep, Monte Carlo mismatch) | 2026-10-06 | Curtis ch. 7 §7.2 (nonlinear relative motion equations); Wie §3.6 (orbital perturbations) or Vallado, 'Fundamentals of Astrodynamics and Applications' — only for the optional terms; SciPy solve_ivp docs (rtol/atol choice). | Not started
21 | Convex modeling of MPC constraints & costs: second-order cone constraints, ‖u‖₂ ≤ u_max vs. box limits, L1/L2 fuel-cost norms vs. quadratic cost, approach cone / line-of-sight as SOC, convexifying the keep-out zone, slack penalties | Tasks 14, 16 (constraint set of the QP/SOCP) | 2026-10-16 | Boyd & Vandenberghe ch. 4 (§4.4: QP and SOCP); CVXPY docs, 'Disciplined Convex Programming' page; rendezvous-MPC papers collected in Task 4 (e.g. Hartley et al., 'Model predictive control system design and implementation for spacecraft rendezvous', Control Eng. Practice, 2012 — verify). | Not started
22 | Monte Carlo methodology: sampling initial conditions & noise, seeded reproducibility (numpy.random.Generator), dispersion/percentile metrics, number of runs vs. confidence, reporting constraint-violation rates | Tasks 20, 34, 41 (robustness studies) | 2026-10-27 | NumPy docs, 'Random Generator'; copy the dispersion-reporting conventions from the papers read in Task 4. | Not started
23 | 6-DoF coupling kinematics: docking-port lever arm (r_dock = r_cm + R·b), velocity/acceleration of an offset point, torques from off-axis thrust, relative pose in LVLH, unit-quaternion norm handling in NMPC | Task 39 (coupled 6-DoF model) | 2027-01-05 | Schaub & Junkins ch. 3–4 (rigid-body kinematics, revisit); Wie ch. 5–6 (kinematics + rigid-body dynamics, §6.10 for the orbit coupling) and §7.4/§7.6 (actuators); Fehse, 'Automated Rendezvous and Docking of Spacecraft' (Cambridge, 2003); coupled 6-DoF MPC papers for proximity operations (collect in Task 37). | Not started
24 | OPTIONAL — Vision-based relative pose estimation: pinhole camera model, PnP / feature-based pose from a known 3D model, pose uncertainty | Task 46 (optional stretch) | 2027-03-24 | Hartley & Zisserman, 'Multiple View Geometry in Computer Vision', ch. 6 (camera models) — verify; OpenCV solvePnP tutorial (docs.opencv.org). | Not started
25 | OPTIONAL — Learning-based MPC: Gaussian-process regression, model-mismatch correction inside MPC, safety via constraint tightening | Task 47 (optional stretch) | 2027-04-10 | Rasmussen & Williams, 'Gaussian Processes for Machine Learning', ch. 2 (free PDF); Hewing et al., 'Learning-based model predictive control: toward safe learning in control', Annu. Rev. Control Robot. Auton. Syst., 2020 — verify. | Not started
Progress summary:
| Topics done | 1
| Topics in progress | 1
| Topics not started | 23
| % complete | 4%

## Target Labs
Priority | Professor | Lab | Research Areas (from EPFL listing) | Why It Fits This Project | Fit Level
1 | Colin Jones | Automatic Control Laboratory 3 (LA3) | Control Systems, Optimization, Robotics & Autonomous Systems, Learning & Decision Systems | MPC is literally their core research output. Your CW→linear MPC→6-DoF NMPC roadmap is a direct, self-contained application case study of what this lab does daily. | PRIMARY
2 | Maryam Kamgarpour | Systems Control and Multiagent Optimization Research | Learning & Decision Systems, Robotics and Autonomous Systems | Optimization-under-constraints is the exact spine of your QP/NMPC formulation work — strong second choice inside the same sub-field as Jones, not a dilution of your pitch. | STRONG
3 | Alireza Karimi | Data-Driven Modelling and Control Group | Data & Network Sciences, Energy Systems, Learning & Decision Systems, Robotics, Theory and Simulation | System identification + robust control. Your noise-robustness testing (Monte Carlo under navigation uncertainty) speaks directly to what this group cares about. | STRONG
4 | Giancarlo Ferrari Trecate | Dependable Control and Decision group (DECAR) | Learning & Decision Systems, Mechanical Engineering, Energy Systems | Distributed/robust control theory overlaps with your feasibility and soft-constraint work. Note from earlier discussion: PI has an Italian academic background (Pavia/Polimi-adjacent), which may make your 110L and rigor easier to contextualize. | STRONG
5 | Andrea Cavallaro | LIDIAP | Imaging & Vision, Learning & Decision Systems, Robotics and Autonomous Systems, Sports Technology | Relevant only if you build the optional Phase 6 vision/pose-estimation stretch goal (Task 46) — that closes the 'Sense' half of the GNC loop for a non-cooperative target. Weaker fit if you stay purely on the control side. | MODERATE
6 | Anja Skrivervik | SCI STI AS Group | Electrical Engineering, Flexible Electronics, Personalized Health, Robotics and Autonomous Systems, Space Technology | Explicit Space Technology tag — useful if you want to keep the ADR framing front-and-center rather than pivoting the pitch fully toward generic autonomous systems. Verify current project focus before listing. | MODERATE
7 | Farhad Rachidi-Haeri | SCI STI FR Group | Electrical Engineering, Energy Systems, Space Technology | Space Technology tag present, but the group's recent work may skew toward EM/energy rather than GNC — check the lab's current project list on epfl.ch before including as one of your 3 choices. | MODERATE (verify first)
Note on the E3 application form:
The E3 form asks for up to 3 lab choices. Recommended combination given your project: 1) Colin Jones (LA3) — primary; 2) Kamgarpour or Karimi — same control/optimization core, not a dilution of the pitch; 3) Ferrari Trecate — still control theory, different flavor (distributed/robust). Keep all 3 inside control & optimization rather than mixing in a vision or space-hardware lab, so the motivation letter tells one coherent story.
Beyond E3 (separate processes, same project transfers directly):
ETH Zürich Robotics Student Summer Fellowship — Robotic Systems Lab (Hutter) or Autonomous Systems Lab (Siegwart). Not part of E3; separate application process and deadline (check ethz.ch directly). Your 6-DoF MPC ADR project is an equally strong pitch there, since both labs value real-time optimization-based control on physical/simulated systems. If E3 doesn't work out, a direct email to a PhD student in either lab (proposing a Master Thesis) is also a standard, lower-barrier path in — worth keeping as a parallel option rather than waiting for E3 results in March.